**Time Schedule**

[I am presenting two optional tables to present the time schedule please let me know which one you think is better]

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Research Year/ Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| #1 | Literature review and preparation of interview layout | | Ethics committee approval and interviewees recruitment | | Conduction of interviews, and transcript interviews | | | Interviews content analysis | | | Presentation of preliminary results in a conference | |
| #2 | Literature review and preparation of survey items | | Ethics committee approval and preparation of survey instrument | | pilot survey | Performing survey and preparing data for analysis | | Survey data analysis | | | Presentation of results in a conference and write first paper | |
| #3 | Literature review and preparation of experimental design | | Ethics committee approval and preparation of experiment instrument | | | Conducting experiment and preparing data for analysis | | Experiment analysis | | | Presentation of results in a conference | |
| #4 | Literature review and preparation of educational intervention | | Ethics committee approval and participants recruitment | | Conducting educational intervention, and data collection | | | Educational intervention data analysis | | | Presentation of results in a conference  Write up final report, and a second paper | |

**Note Explanatory**

* Timetable in each of the four project years will be design according to the main mission of the specific year.
* In each year a literature review will be taken to address the specific mission. A literature review is important in order to design the best suitable interventions that can address the specific research questions.
* Receiving an ethics committee approval will be achieved before performing the study in each year.
* Three months will be dedicated to data analysis in each of the four years

|  |  |  |
| --- | --- | --- |
| Research activity | Start month/year | End month/year |
| Year #1 |  |  |
| Literature review and preparation of interview layout | 10/2023 | 11/2023 |
| Ethics committee approval and interviewees recruitment | 12/2023 | 1/2024 |
| Conduction of interviews, and transcript interviews | 2/2024 | 3/2024 |
| Interviews content analysis | 4/2024 | 6/2024 |
| Presentation of preliminary results in a conference | 7/2024 | 9/2024 |
| Year #2 |  |  |
| Literature review and preparation of survey items | 10/2024 | 11/2024 |
| Ethics committee approval and preparation of survey instrument | 12/2024 | 1/2025 |
| pilot survey | 2/2025 | 2/2025 |
| Performing survey and preparing data for analysis | 3/2025 | 4/2025 |
| Survey data analysis | 5/2025 | 7/2025 |
| Presentation of results in a conference and write first paper | 8/2025 | 9/2025 |
| Year #3 |  |  |
| Literature review and preparation of experimental design | 10/2025 | 11/2025 |
| Ethics committee approval and preparation of experiment instrument | 12/2025 | 2/2026 |
| Conducting experiment and preparing data for analysis | 3/2026 | 4/2026 |
| Experiment analysis | 5/2026 | 7/2026 |
| Presentation of results in a conference | 8/2026 | 9/2026 |
| Year #4 |  |  |
| Literature review and preparation of educational intervention | 10/2026 | 11/2026 |
| Ethics committee approval and participants recruitment | 12/2026 | 1/2027 |
| Conducting educational intervention, and data collection | 2/2027 | 4/2027 |
| Educational intervention data analysis | 5/2027 | 7/2027 |
| Presentation of results in a conference  Write up final report, and a second paper | 8/2027 | 9/2027 |

**Note Explanatory**

* Timetable in each of the four project years will be design according to the main mission of the specific year.
* In each year a literature review will be taken to address the specific mission. A literature review is important in order to design the best suitable interventions that can address the specific research questions.
* Receiving an ethics committee approval will be achieved before performing the study in each year.
* Three months will be dedicated to data analysis in each of the four years