**Time Schedule**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year | study |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| #1 | #1 | Literature review |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of interview layout |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics committee approval |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct interviews |  |  |  |  |  |  |  |  |  |  |  |  |
| Content analysis of interviews |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation of preliminary results at a conference |  |  |  |  |  |  |  |  |  |  |  |  |
| #2 | #2 | Write first paper |  |  |  |  |  |  |  |  |  |  |  |  |
| Literature review and preparation of survey items |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics committee approval |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of survey instrument |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot survey |  |  |  |  |  |  |  |  |  |  |  |  |
| Perform survey |  |  |  |  |  |  |  |  |  |  |  |  |
| Survey data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation of results at a conference |  |  |  |  |  |  |  |  |  |  |  |  |
| #3 | #3 | Preparation of experiment instrument |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics committee approval |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct experiment |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare data for analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation of results at a conference |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write second paper |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Preparation of educational intervention |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Ethics committee approval |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Recruitment |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct educational intervention |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Data collection |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Write up final report |  |  |  |  |  |  |  |  |  |  |  |  |

**Note Explanatory**

* The timetable for each of the four project years is designed according to the main mission of the specific year.
* In each year a literature review will be taken to address the specific mission. A literature review is important in order to design the best suitable interventions that can address the specific research questions.
* Ethics committee approval will be sought before performing the study in each year.
* Three months will be dedicated to data analysis in each of the four years
* Two articles will be written during the four-year project. Time will be devoted to it during the second and the fourth year.