## Sheet1
SAMPLE LISTEN FOR GOOD PROJECT PLAN AND TIMELINE
STEP | TASK | PROJECT MANAGER | LEADERSHIP | STAFF | L4G CONSULTANT | DUE DATE
1. SURVEY DESIGN | Plan Project Milestones using this Plan | √ | √ |  |  | 2019-01-01
| Download and draft survey in Word | √ |  |  |  | 2019-01-08
| Align on survey goals and custom questions with key staff | √ | √ | √ |  | 2019-01-22
| Review custom survey questions with L4G consultant | √ |  |  | √ | 2019-01-29
| Program survey on the L4G website Survey Builder | √ |  |  |  | 2019-02-05
| Create survey in other languages if needed | √ |  |  |  | 2019-02-05
2. SURVEY ADMINISTRATION | Develop data collection plan - communicate & confer with key staff | √ |  | √ |  | 2019-02-12
| Discuss data collection plan with L4G consultant | √ |  |  | √ | 2019-02-12
| Create survey collectors for online and/or paper administration | √ |  |  |  | 2019-02-16
| Set up technology, if needed | √ |  | √ |  | 2019-02-23
| Train staff / volunteers; review client talking points | √ |  | √ |  | 2019-03-02
| Figure out response rate calculation plan | √ |  |  |  | 2019-03-02
DATA COLLECTION | Monitor # of surveys coming in; talk to TA Provider if low response rates | √ |  |  | √ | 2019-03-02
3. INTERPRETING RESULTS | Enter your response rates on the L4G website | √ |  |  |  | 2019-04-01
| Review means and distributions; compare to benchmarks | √ |  |  |  | 2019-04-01
| Analyze qualitative data, using coding | √ |  |  |  | 2019-04-15
| Segment data by demographics + site | √ |  |  |  | 2019-04-22
| Identify key themes: areas for celebration and improvement |  |  |  |  | 2019-04-22
| Share and discuss findings with L4G consultant | √ |  |  | √ | 2019-04-22
4. RESPONDING TO FEEDBACK | Use the Report Builder on L4G website to share survey results with staff | √ | √ |  |  | 2019-04-22
| At internal meetings, review feedback and prioritize areas for improvement | √ | √ | √ |  | 2019-05-06
| Create an Action Plan, available on L4G website | √ | √ | √ |  | 2019-04-23
| Set up call with L4G consultant to discuss changes and preview closing the loop | √ |  |  | √ | 2019-05-07
| Make changes! Start with low hanging fruit | √ |  | √ |  | 2019-05-14
5. CLOSING THE LOOP | Craft messages for clients – keep it short and relevant | √ |  | √ |  | 2019-05-28
| Determine communication channel that works best - leverage existing methods and forums | √ |  | √ |  | 2019-05-28
| Close the Loop with clients | √ |  |  |  | 2019-06-04
| Review Closing the Loop with L4G consultant and discuss next feedback cycle | √ |  |  | √ | 2019-06-11
| Plan for next feedback cycle | √ | √ | √ |  | 2019-06-18
Formulas:
DUE DATE = [DUE DATE, row above]+7
DUE DATE = [DUE DATE, row above]
NOTE: All dates and roles / responsibilities are for example only. While the typical feedback cycle should take 6 months, it can vary based on each organization. In addition, your L4G consultant is available to help you more or less often than listed here based on your needs.
NOTE: Data collection can take anywhere from 1-2 weeks if it's a "one-time" campaign, OR months if you are collecting data on an ongoing basis.