| ## الأهداف والمنهج والجدول الزمني للمشروع يتمثل الهدف من مشروع المساعدة المقدَّم من شركة xxx في التحرك من القائمة المختصرة للمستثمرين المعنيين، وهو الموقع الذي ضمنّاه نتيجة لقيامنا بالمساعدة حتى وقتنا الحاضر ،نحو التوقيع الفعلي للعقد مع المستثمرين الذين وقع عليهم الاختيار، بواقع مستثمر لكل قطعة أرض. ويتطلب هذا بدوره ما يلي: - دعم المستثمرين في تطوير إجاباتهم على طلبات العروض - تعريف معايير ترسية العطاء على "مقدمي العطاءات الفائزين" وتأسيس لجنة تقييم مناسبة - ترسية العطاءات على "مقدمي العطاءات الفائزين". - مسودة العقود المرتقبة بين "مقدمي العطاءات الفائزين" وهيئة التجارة والتنمية (TDA) - الإعداد لمرحلة التفاوض (مثال: فهم الآثار المترتبة على تحركات التفاوض المرتقبة) - دعم عملية التفاوض وتوقيع العقد مع "مقدمي العطاءات الفائزين". يتمثل هدفنا من حيث التوقيت في بدء التفاوض مع "مقدمي العطاءات الفائزين" بحلول فصل الصيف، كما نهدف لتوقيع العقود بحلول نهاية العام. من أجل الوفاء بالأهداف المذكورة أعلاه فإننا نقترح منهجًا يعتمد على أربعة جداول عمل متداخلة جزئيًا (العرض 1). وفي الفقرات التالية يتم وصف جداول العمل الأربعة من حيث الأنشطة الرئيسية والأهداف القابلة للتنفيذ. | ## PROJECT OBJECTIVES, APPROACH AND TIMELINE The objective of McKinsey assistance is then to move from the short list of interested investors, that was secured as result of our assistance so far, to the actual signing of the contract with the selected investors, one for each plot. This, in turn, will require to: - Support the investors in developing their answers to the RFPs - Define the criteria to award the “winning bidders” and set up a proper evaluation committee - Award the “winning bidders”. - Draft potential contracts between the ”winning bidders” and TDA - Prepare the negotiation phase (e.g. understand implications of potential negotiation move) - Support the negotiation and the signing of the contract with the ”winning bidders”. In terms of timing, we aim to launch the negotiation with the “winning bidders” by the summer and to sign the contracts by the end of the year In order to fulfill the aforementioned objectives we propose an approach based on 4 partially overlapping work-streams (Exhibit 1). In the following paragraphs the 4 work-streams are described in terms of main activities and deliverables. |
| --- | --- |